## Sheet1
1. Project Initiation | 10 days | 2025-04-09 08:00 | 2025-04-22 17:00
1.1 Create Project Scope/Goals | 2 days | 2025-04-09 08:00 | 2025-04-10 17:00 |  | Project Manager
1.2 Explain who the Stakeholders are | 3 days | 2025-04-11 08:00 | 2025-04-15 17:00 | 2 | Business Analysts
1.3 Create the overall project plan | 3 days | 2025-04-16 08:00 | 2025-04-18 17:00 | 3 | Project Manager;Senior Developers
1.4 Assign the roles to each corresponding team | 2 days | 2025-04-21 08:00 | 2025-04-22 17:00 | 4 | HR/Project Manager
2. Requirement Analysis | 11 days | 2025-04-23 08:00 | e
2.1 Find/Identify our competitors | 5 days | 2025-04-23 08:00 | 2025-04-29 17:00 |  | Project Manager
2.2 Identify the user personas | 3 days | 2025-04-23 08:00 | 2025-04-25 17:00 | 1 | Product Owner
2.3 Identify the app features | 3 days | 2025-04-30 08:00 | 2025-05-02 17:00 | 7;8 | Lead Developer;Product Owner
2.4 Find implementation resources | 2 days | 2025-05-05 08:00 | 2025-05-06 17:00 | 9 | Business Analyst;Product Owner
2.5 Find non-implementation resources such as security, performance, etc | 3 days | 2025-05-05 08:00 | 2025-05-07 17:00 | 9 | Business Analyst
3. Design Phase | 17 days | 2025-05-08 08:00 | 2025-05-30 17:00
3.1 Create our System | 5 days | 2025-05-08 08:00 | 2025-05-14 17:00 |  | Lead Developer
3.2 Create a schematic for our database | 4 days | 2025-05-15 08:00 | 2025-05-20 17:00 | 13 | Database Architect
3.3 Create the wireframes/mockups for our User Interface | 5 days | 2025-05-15 08:00 | 2025-05-21 17:00 | 13 | UI/UX Designer
3.4 User experience (UX) | 7 days | 2025-05-22 08:00 | 2025-05-30 17:00 | 15 | UX Designer
3.5 Create User Interface | 7 days | 2025-05-22 08:00 | 2025-05-30 17:00 | 15 | UI/UX Designer
3.6 Finalize architecture for our API | 3 days | 2025-05-21 08:00 | 2025-05-23 17:00 | 14 | Backend Developer;Lead Developer
3.7 Discuss a plan for social media | 2 days | 2025-05-15 08:00 | 2025-05-16 17:00 | 13 | Product Owner;Social Media Expert
4. Development Phase | 64 days? | 2025-06-02 08:00 | 2025-08-28 17:00
4.1 Setup | 5 days? | 2025-06-02 08:00 | 2025-06-06 17:00
4.1.1 Plan social media implementation | 1 day | 2025-06-02 08:00 | 2025-06-02 17:00 |  | DevOps;Lead Developer
4.1.2 Create Github Repo's | 2 days | 2025-06-02 08:00 | 2025-06-03 17:00 |  | Backend Developer;DevOps
4.1.3 Set up a proper environment for development | 5 days? | 2025-06-02 08:00 | 2025-06-06 17:00 |  | AI Specialist;Data Scientist
4.2 AI Model Pipeline | 35 days | 2025-06-09 08:00 | 2025-07-25 17:00
4.2.1 Construct a dataset with types of food | 10 days | 2025-06-09 08:00 | 2025-06-20 17:00 |  | Data Scientist
4.2.2 Construct a food recognition model using a CNN | 4 days | 2025-06-23 08:00 | 2025-06-26 17:00 | 26 | Data Scientist;Researcher
4.2.3 Train the model to be able to recognize the food | 7 days | 2025-06-27 08:00 | 2025-07-07 17:00 | 27 | Tester
4.2.4 Test the model | 10 days | 2025-07-08 08:00 | 2025-07-21 17:00 | 28 | Backend Developer
4.2.5 Implement the food recognition model | 4 days | 2025-07-22 08:00 | 2025-07-25 17:00 | 29 | Admin;Backend Developer
4.3 Model Integration & Meal Scan Feature | 5 days | 2025-07-28 08:00 | 2025-08-01 17:00
4.3.1 Integrate database with the food recognition model | 5 days | 2025-07-28 08:00 | 2025-08-01 17:00 | 30 | Backend Developer
4.3.2 Construct a system where the user can image scan a meal | 3 days | 2025-07-28 08:00 | 2025-07-30 17:00 | 30 | Backend Developer;Nutritionist
4.3.3 Implement a feature that can recognize public meals | 3 days | 2025-07-28 08:00 | 2025-07-30 17:00 | 30 | Backend Developer;Frontend Developer
4.4 User Authentication | 22 days | 2025-06-09 08:00 | 2025-07-08 17:00
4.4.1 Construct a safe and strong user authentication | 3 days | 2025-06-09 08:00 | 2025-06-11 17:00 | 21 | Backend Developer;Frontend Developer
4.4.2 Construct a profile management system | 4 days | 2025-06-09 08:00 | 2025-06-12 17:00 | 21 | Backend Developer;Frontend Developer
4.4.3 Construct the data protection, encryption, and security parts | 22 days | 2025-06-09 08:00 | 2025-07-08 17:00 | 21 | Mobile Developer;UI/UX Designer
4.5 Meal Logging & Analysis System | 19 days | 2025-08-04 08:00 | 2025-08-28 17:00
4.5.1 Construct a system to track/count calories | 6 days | 2025-08-04 08:00 | 2025-08-11 17:00 | 31 | Mobile Developer
4.5.2 Construct a system to macronutrients | 4 days | 2025-08-04 08:00 | 2025-08-07 17:00 | 31 | Backend Developer;Frontend Developer
4.5.3 Implement meal tracking functionality | 3 days | 2025-08-12 08:00 | 2025-08-14 17:00 | 40;41 | Backend Developer;Frontend Developer
4.5.4 Create a feature that recommends a meal to eat every week | 10 days | 2025-08-15 08:00 | 2025-08-28 17:00 | 42 | Backend Developer
4.6 Monetization & Admin Control | 14 days | 2025-07-09 08:00 | 2025-07-28 17:00
4.6.1 Construct a payment plan for higher access to the app | 5 days | 2025-07-09 08:00 | 2025-07-15 17:00 | 35 | Backend Developer;Frontend Developer
4.6.2 Build a notification system | 14 days | 2025-07-09 08:00 | 2025-07-28 17:00 | 35 | Backend Developer
4.6.3 Create admin panel for managing users and meals | 7 days | 2025-07-09 08:00 | 2025-07-17 17:00 | 35 | Backend Developer;Security Expert
4.7 App UI | 24 days | 2025-07-28 08:00 | 2025-08-28 17:00
4.7.1 Develop the mobile and app interface | 24 days | 2025-07-28 08:00 | 2025-08-28 17:00 | 30 | UI/UX Designer;Web Developer
4.8 Social Features | 10 days | 2025-06-03 08:00 | 2025-06-16 17:00
4.8.1 Implement the social media plan from task 1 | 4 days | 2025-06-03 08:00 | 2025-06-06 17:00 | 22 | Backend Developer;Frontend Developer
4.8.2 Construct a system to involve users such as a point system | 3 days | 2025-06-12 08:00 | 2025-06-16 17:00 | 36 | Backend Developer;Frontend Developer
5. Testing Phase | 43 days | 2025-08-29 08:00 | 2025-10-28 17:00
5.1 Build the testing units | 3 days | 2025-08-29 08:00 | 2025-09-02 17:00 | 20 | QA Developer;QA Tester
5.2 Run functional/unit tests | 3 days | 2025-09-03 08:00 | 2025-09-05 17:00 | 54 | Backend Developer;QA Tester
5.3 Systems integration testing | 4 days | 2025-09-08 08:00 | 2025-09-11 17:00 | 55 | QA Developer;QA Tester
5.4 Load and performance testing | 3 days | 2025-09-12 08:00 | 2025-09-16 17:00 | 56 | QA Tester
5.5 Test the system with beta access users | 11 days | 2025-09-17 08:00 | 2025-10-01 17:00 | 57 | QA Tester
5.6 Collect and analyze feedback from beta users | 30 days | 2025-09-17 08:00 | 2025-10-28 17:00 | 58SS | QA Tester
5.7 Bug Fixing | 30 days | 2025-09-17 08:00 | 2025-10-28 17:00 | 58SS | QA Tester
6. Deployment Phase | 17 days | 2025-10-31 08:00 | 2025-11-24 17:00
6.1 Prepare deployment environment | 2 days | 2025-10-31 08:00 | 2025-11-03 17:00 | 53 | Backend Developer;DevOps
6.2 Deploy backend to production | 2 days | 2025-11-04 08:00 | 2025-11-05 17:00 | 62 | Backend Developer;DevOps
6.3 Deploy web/mobile to production | 2 days | 2025-11-04 08:00 | 2025-11-05 17:00 | 62 | DevOps;Frontend Developer;Mobile Developer
6.4 Set up monitoring tools such as our error tracking system | 2 days | 2025-11-06 08:00 | 2025-11-07 17:00 | 63;64 | Backend Developer;DevOps
6.5 Perform a final round testing | 5 days | 2025-11-10 08:00 | 2025-11-14 17:00 | 65 | QA Tester
6.6 Construct marketing plans | 3 days | 2025-11-17 08:00 | 2025-11-19 17:00 | 66 | Marketing Team;Product Owner
6.7 Plan a system that will find new updates | 1 day | 2025-11-17 08:00 | 2025-11-17 17:00 | 66 | Backend Developer;Frontend Developer;Product Owner
6.8 Fill out the documents for the app store | 3 days | 2025-11-20 08:00 | 2025-11-24 17:00 | 67 | Marketing Team;Product Owner
7. Post-Launch Phase | 23 days | 2025-11-25 09:00 | 2025-12-26 09:00
7.1 Monitor the app's performance | 14 days | 2025-11-25 09:00 | 2025-12-15 09:00 | 61 | Backend Developer;DevOps
7.2 Analyze our user comments/feedback | 14 days | 2025-11-25 09:00 | 2025-12-15 09:00 | 61 | Customer Support;Marketing Team;Product Owner
7.3 Analyze how many users are engaged | 14 days | 2025-11-25 09:00 | 2025-12-15 09:00 | 61 | Data Analyst;Product Owner
7.4 Address performance or feedback issues | 7 days | 2025-12-15 09:00 | 2025-12-24 09:00 | 71;72;73 | Backend Developer;DevOps
7.5 Update the app and websites | 2 days | 2025-12-24 09:00 | 2025-12-26 09:00 | 74 | Backend Developer;Frontend Developer;Product Owner
8. Maintenance Phase | 28 days | 2025-11-25 09:00 | 2026-01-02 09:00
8.1 Monitor the system and user logs | 14 days | 2025-11-25 09:00 | 2025-12-15 09:00 | 61 | Backend Developer;DevOps
8.2 Build a system within the company to have database maintenance | 14 days | 2025-11-25 09:00 | 2025-12-15 09:00 | 61 | Backend Developer;Database Admin
8.3 Constantly update the new food items | 28 days | 2025-11-25 09:00 | 2026-01-02 09:00 | 61 | Backend Developer;Database Admin